## Software
TASK	UI	DEV	TOTAL
Authentication
Login	1	2	3
Forgot Password	1	2	3

Users
Create	1.5	1.5	3
Edit	2	2	4
Delete	0	0.5	0.5
Permissions	2	4	6

Items
Create	1.5	1.5	3
Edit	2	2	4
Delete	0	0.5	0.5
Upload Image	0	1	1

Item Categories
Create	1.5	1.5	3
Edit	2	2	4
Delete	0	0.5	0.5
Upload Image	0	1	1

Sales
Save Temporarily	6	6	12
Save Permanently	0	1	1
Delete from Temporary	0	1	1
Delete from Permanent	0	1	1

Clients
Create	1.5	1.5	3
Edit	2	2	4
Delete	0	0.5	0.5
Upload Image	0	1	1

Reports
Sales
Per Month, Year, Custom Range	2	4	6
Products
Best Seller	2	4	6

TOTAL HOURS			72
TOTAL WEEKS			3

## Hardware
ITEM	PRICE	QTY	AMOUNT
Laptop Acer Inspire i3 11th Gen	27,000.00	1.00	27,000.00		3yrs warranty
POS Printer	8,000.00	1.00	8,000.00
Drawer	4,000.00	0.00	0.00
Tablet Lenovo 10in	16,000.00	1.00	16,000.00
iPad 9th Gen	25,990.00	0.00	0.00
iPad 10th Gen	27,990.00	0.00	0.00
TOTAL			51,000.00